## Application_Matrix
Requirment | Support Ticketing | Deal Modeler | Probation Management | Exit Management | IAMS
Staging Environment | 1. http://ec2-18-159-76-133.eu-central-1.compute.amazonaws.com/ticket_htschedule/ 2. http://ec2-18-159-76-133.eu-central-1.compute.amazonaws.com/ticket_latest_may2024 | 1. http://35.157.208.9/dm_archived/user/login/ http://35.157.208.9/dm_demo_calc/ 2. http://35.157.208.9/dm_latest/user/login | No | 1. http://35.157.208.9/sent_staging/
Data available for testing | Yes | Yes | No | Yes

## Support_Ticketing
Feature Name | Requirment Details | Dev Status | QA Status | Comments
2024-02-01
Category Level Access | Develop the Category level access Agent should have access based on Category not based on Department | Ready for QA | Re-Open - 12Feb | If Agent don't have access to any department/category then upon Export system should list any tickts
2024-03-01
IAMS Category | Add the IAMS Category into Corporate Department for IND and USA Location | Done | Hold | Veeresh - Access need to give Public ? Adding is done. Vinyas said - will enable from next month

## DM
Feature Name | Requirment Details | Dev Status | QA Status | Comments
Febuary 2024
Upload Documents | Develop the Upload document functionality for Create Deal | Ready for QA | Closed | Working as Expected

## PM
Feature Name | Requirment Details | Dev Status | QA Status | Comments
2024-02-01
Probation Feature | Develop the Probation Management System | Ready for QA | Re-Open | Raised some issue on 8th March.

## IAMS
Feature Name | Requirment Details | Dev Status | QA Status | Comments
2024-02-01
User Manual Guide for User Application | Draft all the flow of the user application | Done | Closed
User Manual Guide for Admin Console | Draft all the flow of the Admin Consloe | Done | Closed
IAMS Application | Develop the IAMS Application | Released | Closed

## Intranet
Feature Name | Requirment Details | Dev Status | QA Status | Comments